## Tracker
[12 empty] | Revision : | A
Part No: | A5060-21 | [10 empty] | Revised Date: | 2012-05-03
Description: | CASING HGR,MS-700,18.750 X 13.375,13.375 68 LB/FT VAM TOP BOX,10000 PSI MWP,HAS TAPERED SEAL POCKET
FOR 13.500 HGR STACKUP SYSTEM
ITP | In Process | MPP | In Process | M/C Tools | In Process | QA Tools | In Process | Fixture | In Process
Status: | 100% | Status: | 100% | Status: | 100% | Status: | 100% | Status: | 0%
Target Date: |  | Target Date: |  | Target Date: |  | Target Date: |  | Target Date:
Project No: | Casing Hanger New |  | PO Number: | PX14846-2
Work Order: |  |  | Req Del Date: | 2012-05-15
Qty: | 1
Del Date: | 2012-05-14 22:48
Material : | Yes |  | Custom Doc: | Done
Operation Seq No. | Operation Text |  |  | Work Centre | Setup Time Hrs | Est Run Time Hrs | Working Hrs/Day | Req Days | Down Time Hrs | Start Date | End Date | Status | Remarks
10 | Rough OD |  |  | YB 5506 | 2 | 4 | 20 | 0.3 | 0 | 2012-05-04 | 2012-05-04 07:12
20 | Rough OD & ID |  |  | YB 5506 | 2 | 4 | 20 | 0.3 | 0 | 2012-05-04 07:12 | 2012-05-04 14:24
30 | Finishing OD & ID |  |  | YB 5506 | 2 | 4 | 20 | 0.3 | 0 | 2012-05-04 14:24 | 2012-05-04 21:36
40 | Drilll Holes |  |  | HSA4260 | 4 | 18 | 20 | 1.1 | 0 | 2012-05-04 21:36 | 2012-05-06
50 | Slot Milling |  |  | HSA4260 | 4 | 4 | 20 | 0.4 | 0 | 2012-05-06 | 2012-05-06 09:36
60 | Deburing |  |  | Prod | 0 | 4 | 20 | 0.2 | 0 | 2012-05-06 09:36 | 2012-05-06 14:24
70 | QA Inspection |  |  | QA | 0 | 4 | 20 | 0.2 | 0 | 2012-05-06 14:24 | 2012-05-06 19:12
80 | Hardness Test |  |  | QA | 0 | 1 | 20 | 0.05 | 0 | 2012-05-06 19:12 | 2012-05-06 20:24
90 | NDT VGS8.3.2-S1 |  |  | Nov | 0 | 20 | 20 | 1 | 0 | 2012-05-06 20:24 | 2012-05-07 20:24 |  | Export 2 way
100 | Shrink Fit Process |  |  | Jemix | 0 | 20 | 20 | 1 | 0 | 2012-05-07 20:24 | 2012-05-08 20:24 |  | Subcon
110 | Facing & OD Finishing |  |  | YB 5506 | 2 | 2 | 20 | 0.2 | 0 | 2012-05-08 20:24 | 2012-05-09 01:12
120 | Vam Thread Cutting |  |  | OMS | 0 | 60 | 20 | 3 | 0 | 2012-05-09 01:12 | 2012-05-12 01:12 |  | Export one way
130 | NDT VGS8.3.2-S1 |  |  | Nov | 0 | 20 | 20 | 1 | 0 | 2012-05-12 01:12 | 2012-05-13 01:12
140 | QA Inspection |  |  | QA | 0 | 4 | 20 | 0.2 | 0 | 2012-05-13 01:12 | 2012-05-13 06:00
170 | Stressless Stamp |  |  | Prod | 0 | 1 | 20 | 0.05 | 0 | 2012-05-13 06:00 | 2012-05-13 07:12
150 | Phosphating VGS 6.2.3.2 |  |  | M&R Scientific | 2 | 3 | 20 | 0.25 | 0 | 2012-05-13 06:00 | 2012-05-13 12:00
160 | Hardness Test |  |  | QA | 0 | 1 | 20 | 0.05 | 0 | 2012-05-13 12:00 | 2012-05-13 13:12
170 | Assemble Shipping Protector 18-3/4 MS 600 |  |  | Prod | 0 | 4 | 20 | 0.2 | 0 | 2012-05-13 13:12 | 2012-05-13 18:00
180 | Stencil on Protector |  |  | Prod | 0 | 4 | 20 | 0.2 | 0 | 2012-05-13 18:00 | 2012-05-13 22:48
190 | Final QA & Shipping |  |  |  | 0 | 20 | 20 | 1 | 0 | 2012-05-13 22:48 | 2012-05-14 22:48
|  |  |  | Total | 18 | 202 |  | 11 | 0
Critical Issues:
Comments:
Formulas:
End Date = [Start Date]+([In Process]/24)+[Fixture]
Start Date = [End Date, row above]
M&R Manufacturing Sdn Bhd
Marketing
Engineering
Production
Quality